## Team details
Team Name | Boycott
Team Size | 5
Member 1 | G Srihari
Member 2 | K Darshan Raj Kumar
Member 3 | K Prem Kumar
Member 4 | GVP Varun
Member 5 | B Lokesh
Scrum master | G Srihari
Product Owner | M. Venkatesh
Project Start Date | 2022-12-26
Project End Date | 2023-01-21
Project Title | Online Hospital Appointment Application
Number of Sprints | 4
Duration per sprint | 1-Week
No of hours spent by each member per sprint | 42 hrs
Total number of hours spent by all members | 840hrs
Review by experts

## Working agreement
Duration of sprint | 1 week
Time of daily scrum | 10mins
Place of daily scrum | College

## Definition of done
Every item of pb should satisfy the below dod
S.No. | CheckList
1 | All acceptance criteria should pass
2 | no open defects
3 | fundamental documentation should be done (either late or continuous)
4 | Integration testing should be done
5 | Code review must be done and feedback must be implemented

## Backlog Sheet
Order/Priority | Backlog item description | Remarks | Dependency of backlog item on another
1 | Read the entire Use Case and Understood the User Story, prepared a high level design which includes Application structure, Organization Structure (including Actors, Access Groups and Operators) and Requirements. | Completed | No Dependency
2 | Application Creation | Completed | 1
Create Hospital Appointment as Implemention structure of Application
Create organization , division and unit records
Create Access groups
Create Operator
3 | Creating Case lifecycle | Completed | 1
Create Browse Your Appointment Case Lifecycle
Create Admin Case Lifecycle and Services Case Type
4 | Create Data types | Completed | 1
Create data types such as Dentist, Dermatology, General Physician, NewHomeopathy, Patient Details, TimeSlot
5 | Design UI forms and Validations
5A | Design UI forms for Browse Your Pet(Home Page, Doctor Appointmnet, My Appoinments, Collect Patient Details, Collect Doctor Details, Feedback ) | Completed | 3,4
5B | Design UI forms for Services(Choose Appoinment,View Doctor Details, Appointments, Feedback )
5C | Design UI form for Add Items(Modify Records Form, Add Records Form, View Forms, Delete Form) | Completed | 3,4
6 | Process Design
| Browse your Pet i. Home Page - (How it Works, Contact, Doctor Registration, User Registration) ii. Book Appointment iii.Details of the Patient and Doctor. iv.Wait for the approval of the Receptionist. v.After successful approval. vi. The Appointment will be Booked. | Completed | 3,4
Add Items
| i. To add or delete Appointment records. ii.If the add record is selected then add the Appoinment details. iii.If the delete record is selected then delete the record in Appointment details. | Completed
7 | Created Dynamic Operator for Customer | Completed | 1
8 | User Interface for Case types | Completed | 3
9 | Portals Creation | Completed | 3
| Customer Portal | Completed | 3
| Receiptionist Portal | Completed | 3
| Doctor Portal | Completed | 3
11 | End to End Testing | Completed | 2

## Sprint1
1 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Read the entire use case and prepare a high level design | Creating High Level Design which includes Application structure, Organization Structure (including Actors, Operators and Access Groups) |  | Completed | Requirements Discussion | Understanding all the requirments and mind sharing | 3 | 3 | 0 | Completed | 3
|  |  |  | Organization Structure | Identify Organization divisions, units | 2 | 2 | 0 | Completed | 1
|  |  |  | Case Type Identification | Identify required case type | 1 | 1 | 0 | Completed | 1
|  |  |  | Data Model | Identify all the required data types and draw the data model design | 5 | 5 | 0 | Completed | 2
Backlog item 2 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Application Creation | Creating application, organization, access groups, operator IDs |  | Completed | Application Creation | Creating application, organization, access groups, operator IDs | 1 | 1 | 0 | Completed | 1
Backlog item 3 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Case Design | Creating Case Types |  | Completed | Case Design | Case life cycle for Browse Your Appointment | 7 | 7 | 0 | Completed | 2
Backlog item 4 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Data Design | Creating all the data types |  | Completed | Data Design | Creating data types Dentist, Dermatologist, General Physician, New Homeopathy, Patient Details, TimeSlot | 2 | 2 | 0 | Completed | 2

## Sprint2
Backlog item 5A |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Created UI in Browse Your Appointment | Creating UI screens with appropriate validations and customize harness for Browse Your Appointment Case type |  | Completed | Created Properties | Created Properties required | 1hr | 1hr | 0 | Completed | 2
|  |  |  | Created Data Pages & Report Defination | Created a Report Defination and used Fillter Condition to Fetch the Data from Local Data Source based on Parameters. | 30 min | 30 min | 0 | Completed
|  |  |  | Created sections | Created Section for "Home Page" (Segmented Buttons to Shop a Pet, Pet Accessories and or Pet Food) and Configured a Repeated Dynamic Layout to fetch the available Pets from Local Data Source using Data Page and Report Defination | 1 | 1 | 0 | Completed
[5 empty] | Created Section for "Shop Item " and Configure Add to Cart in Layout Group Tabbed View & Can Continue Shopping If user wants to shop accessories, Food | 2 | 2 | 0 | Completed
[5 empty] | Created Section for entering Address Details | 1 | 1 | 0 | Completed
[5 empty] | Created a Section for Make Payment and Added a Button (Created an Action Set "Open URL in Window" to open the Payment Site) | 1 | 1 | 0 | Completed
[5 empty] | Created a Section for Feedback to Display the Ratting as Stars and Feedback | 1 | 1 | 0 | Completed
|  |  |  | Created Data Transform | Created a Data Transform to Copy the Data from pyWorkPage to Local Data Source | 1 | 1 | 0 | Completed
|  |  |  | Created Savable Data Page | Created Savable Data Pages Source as Data Transform to save the Details in the Local Data Source(Pets Data savable) | 30 min | 30 min | 0 | Completed
Backlog item 5B |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Created UI in Register Case Type | Creating UI screens with appropriate validations and customize harness for Register Case Type |  | Completed | Created Properties | Created Properties required | 1hr | 1hr | 0 | Completed | 2
|  |  |  | Created Data Pages & Report Defination | Created a Report Defination and used Fillter Condition to Fetch the Data from Local Data Source based on Parameters. | 30 min | 30 min | 0 | Completed
|  |  |  | Created sections | Created Section f | 1 | 1 | 0 | Completed
[5 empty] | Created Section for "Service Details" and Configure the Layout Group and the repeating dynamic layout. | 1 | 1 | 0 | Completed
[5 empty] | Created Section for " View Services Cart" and Configure the Tabbed Layout Group for selection of Services. | 1 | 1 | 0 | Completed
[5 empty] | Created a Section for Make Payment and Added a Button (Created an Action Set "Open URL in Window" to open the Payment Site) | 1 | 1 | -30min | Completed
[5 empty] | Created a Section for Feedback to Display the Ratting as Stars and Feedback | 1 | 1 | 0 | Completed
|  |  |  | Created Data Transform | Created a Data Transform to Copy the Data from pyWorkPage to Local Data Source | 1 | 1 | 0 | Completed
|  |  |  | Created Savable Data Page | Created Savable Data Pages Source as Data Transform to save the Details in the Local Data Source(Pets Data savable) | 30 min | 30 min | 0 | Completed
Tasks
Backlog item 5C |  |  |  | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Name | Description | Size | Status | Created Properties | Created required properties. | 30 min | 30 min | 0 | Completed | 1
Created UI in Doctor Case Life Cycle | Creating UI screens with appropriate validations and customize harness for Doctor Case Life Cycle |  | Completed |  | Created Properties to Modify records. | 1 | 1 | 0 | Completed
|  |  |  | Created a section | Created a section to add records and Delete Records | 2 hour | 2 hour 30 minutes | -30 minutes | Completed
[5 empty] | Created a Savable Data Pages To add Records and written an Activity to delete records | 1 | 2 | 0 | Completed
|  |  |  | Created Data Transform | Created a Data Transform to Copy the Data from pyWorkPage to Local Data Source | 15 minutes | 15 minutes | 0 | Completed

## Sprint 3
Backlog item 6
Name | Description | Size | Status | Tasks
Process | Creating Process Design for Browse Your Pet Case type and Services Case life Cycle |  | Completed | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
|  |  |  | Created Properties | Created Properties required | 1hr | 1hr | 0 | Completed | All
|  |  |  | Created Data Pages & Report Defination | Created a Report Defination and used Fillter Condition to Fetch the Data from Local Data Source based on Parameters. | 30 min | 30 min | 0 | Completed
|  |  |  | Created sections | Created Section for "Home Page" (Segmented Buttons to Shop a Pet, Pet Accessories and or Pet Food) and Configured a Repeated Dynamic Layout to fetch the available Pets from Local Data Source using Data Page and Report Defination | 1 | 1 | 0 | Completed
[5 empty] | Created Section for "Shop Item " and Configure Add to Cart in Layout Group Tabbed View & Can Continue Shopping If user wants to shop accessories, Food | 1 | 1 | 0 | Completed
[5 empty] | Created Section for entering Address Details | 1 | 1 | 0 | Completed
[5 empty] | Created Section for "Choose A Service" (Segmented Buttons to a Grooming,Training,Healthcare,Caretaker) and Configured a Repeated Dynamic Layout to fetch the Services Details from Local Data Source using Data Page and Report Defination | 1 | 1 | 0 | Completed
[5 empty] | Created Section for "Service Details" and Configure the Layout Group and the repeating dynamic layout. | 1 | 1 | 0 | Completed
|  |  |  | Created Data Transform | Created Section for " View Services Cart" and Configure the Tabbed Layout Group for selection of Services. | 1 | 1 | 0 | Completed
|  |  |  | Created Savable Data Page | Created Savable Data Pages Source as Data Transform to save the Details in the Local Data Source(Pets Data savable) | 30 min | 30 min | 0 | Completed
Backlog item 7 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Dynamic Operator | Dynamic Operator for Customer |  | Completed | Dynamic Operator | Created Dynamic Operator for Customer | 2 hrs | 2 hrs | 0 | Completed | 1

## Sprint 4
Backlog item 8 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
UI | User Interface for Case types |  | Completed | UI | Created User Interface for three Case types | 5hrs | 4hrs | 1 | Completed | 3
Backlog item 9
Name | Description | Size | Status | Tasks
Portals | Portals Creation |  | Completed | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
|  |  |  | Customizing Portals | Created Portals for Customer,Warehouse Manager and Application Admin | 4hrs | 4hrs | 0 | Completed | 2
Backlog item 11 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Unit Testing | End to End Testing |  | Completed | Unit Testing | End to End Testing | 4hrs | 4hrs | 0 | Completed | 4

## Sprint Review
Sprint Number | Review Comments | To be added to backlog or not
| need more details in the pet grooming section | Yes